## Project Tracker
PROJECT TRACKER — Q3 WEBSITE REDESIGN
Maintained by Mary Rose Anonat — Executive & Personal Support Virtual Assistant
Task | Owner | Status | Priority | Due Date | Notes
Finalize sitemap | A. Domingo | Done | High | 2026-06-20 | Approved by client
Wireframe homepage | A. Domingo | Done | High | 2026-06-24
Write homepage copy | M. Anonat | In Progress | High | 2026-06-30 | Draft shared for review
Design product page | A. Domingo | In Progress | Medium | 2026-07-03
Set up staging server | R. Tan | Not Started | Medium | 2026-07-05 | Waiting on hosting access
Client review – round 1 | M. Anonat | Not Started | High | 2026-07-08 | Schedule call
SEO meta descriptions | M. Anonat | Not Started | Low | 2026-07-10
QA testing – desktop | R. Tan | Not Started | Medium | 2026-07-14
QA testing – mobile | R. Tan | Not Started | Medium | 2026-07-14
Launch | M. Anonat | Not Started | High | 2026-07-18 | Pending final sign-off
Total tasks: | 10
Completed: | 2
% complete: | 20%