## Slide 1
Q3 PLANNING OVERVIEW
Prepared for the leadership team
Prepared by Mary Rose Anonat — Executive & Personal Support Virtual Assistant

## Slide 2
AGENDA
01
Q2 Results Recap
What worked, what didn't
02
Q3 Priorities
Top 3 focus areas for the quarter
03
Resourcing Plan
Team capacity and hiring needs
04
Key Dates & Milestones
What's due and when

## Slide 3
Q3 PRIORITIES
Launch Website Redesign
Modernize brand presence and improve lead capture across all pages.
65% complete
Expand Client Onboarding
Reduce time-to-value for new clients from 3 weeks to 1 week.
30% complete
Improve Reporting Cadence
Move from monthly to bi-weekly stakeholder updates.
10% complete

## Slide 4
KEY DATES & MILESTONES
MILESTONE | OWNER | DATE
Website wireframes approved | A. Domingo | Jul 5
Onboarding workflow v2 live | M. Anonat | Jul 18
Bi-weekly reporting starts | M. Anonat | Jul 1
Q3 mid-quarter review | Leadership team | Aug 15
Website launch | A. Domingo / R. Tan | Sep 1